## Slide 1: Human API Business Review
Concept and local MVP review: current progress, evidence, value assumptions, decisions, and a proposed path to a safe pilot.
Review date · 27 October 2026
Future of Work @ Presight
Notes: Purpose: leadership review of the Human API concept and local synthetic-data prototype. Status is presented as of 27 October 2026; project evaluation inputs were last recorded on 26 October. Sources: README.md, docs/READER_GUIDE.md, and the Idea Document.

## Slide 2: Human API: concept and local MVP review
Agenda
01 | Executive view and decision | Decision
02 | Product and roadmap status | Progress
03 | Evaluation and safety | Evidence
04 | Business case | Assumptions
05 | Required decisions | Leadership
06 | Outlook and risks | Pilot gate
Notes: This agenda separates current evidence from assumptions and decisions. It is a concept-stage readout, not a quarterly operating review based on employee or customer performance data.

## Slide 3: Prove safety and value before a pilot
The local demo runs the question flow using fictional employees and files. It checks owner policy and requester access, cites evidence, routes gaps to a person, and requires approval before reusing corrections.
Project status
The scripted checks pass, but there is no measured employee value, live Microsoft tenant, or real-user pilot.
The single most important insight
Executive Summary
Sponsor a security and privacy review, then confirm each person can access only files their work account permits. Choose one willing team and use non-sensitive files.
Leadership decision required
Local MVP
Bottom line
The base estimate is AED 700k in time value versus AED 740k in annual cost. The AED 40k gap is illustrative; time value is not cash savings.
Notes: Sources: PROGRESS.md and evaluations/latest_results.json (17 backend tests; 36 written search cases passed), plus the illustrative model in the Business Case. There is no live user, tenant, or productivity result.

## Slide 4: What is proven so far—and what is not
Question records, owner rules, file checks, cited answers, escalation, and correction approval run locally.
The local app demonstrates the workflow on fictional data. Microsoft connections and employee value remain unproven.
Current position
Working workflow
17 backend tests and 36 of 36 written search cases passed. No real employees or tenant were tested.
Synthetic checks
50,000 possible annual questions and AED 700k base time value are planning assumptions, not measured results.
Illustrative value
Microsoft sign-in and file access are not connected or tested in a work account. There is no Teams app or language model.
Microsoft readiness
Notes: Sources: README.md, DEMO_GUIDE.md, PROGRESS.md, and evaluations/latest_results.json. The test set is synthetic; zero access violations refers only to the scripted cases, not a real Microsoft tenant.

## Slide 5: Business outcomes have not yet been measured
The local app demonstrates a question being saved, checked against owner and requester permissions, answered with a source, or routed to a person.
17 backend tests and all 36 written retrieval cases passed. These small fictional fixtures do not prove production accuracy, security, or value.
Current evidence is prototype-level
Question handling and approval run with synthetic people and files.
Local workflow
17 backend tests and 36 search examples passed.
Scripted checks
No employee pilot, tenant proof, or time-savings study yet.
No live outcomes
Notes: Sources: local demo scope in README.md and the Evaluation Report. Test pass counts describe expected local behavior; they do not establish answer quality, security certification, user adoption, or business impact.

## Slide 6: Three controls keep the workflow governed
Requester access
Owner consent never gives another person new file access.
Human fallback
Missing or conflicting evidence goes to an approved person; reuse waits for owner approval.
Owner opt-in
The owner chooses the scope and can pause or revoke the policy.
Owner consent limits dates, projects, topics, audience, and selected sources.
The requester must already be allowed to open a file. Access is checked before search and again before a saved answer is shown.
Before any file is used
Notes: Sources: docs/SECURITY_ARCHITECTURE.md and docs/TECHNICAL_DESIGN.md. Owner consent and requester file permission are separate controls. Microsoft delegated access is planned but not tenant-tested.

## Slide 7: Strategic focus: connect before building more
Existing tools already search files, cite sources, and respect permissions.
Possible gap: owner-approved deadlines, source limits, human handoff, and approved reuse.
First test this workflow inside Teams or Copilot Studio.
Can Microsoft tools configure this same lifecycle at lower cost?
Compare a configured workflow with the Human API prototype before funding a standalone service.
Public vendor claims change; recheck availability and licensing before a decision.
Test a narrow handoff workflow on top of search tools already in use.
Notes: Source: docs/COMPETITIVE_ANALYSIS.md, reviewed 26 October 2026. Vendor capabilities and licensing can change; the slide frames the product distinction as a hypothesis and recommends comparison with Microsoft configuration.

## Slide 8: The idea looks useful; its unique value is unproven
Human API should manage a controlled handoff around existing file search, not become another search engine. The next step should test whether owner permission, each person's existing file access, source citations, and human review solve a problem Microsoft tools cannot solve at lower cost.
Notes: This is the product hypothesis, not a claim that Human API is unique or that current Microsoft tools cannot deliver the workflow. Validate with customer interviews and a configuration proof of concept.

## Slide 9: Scorecard: demo checks, not real-world results
Measure | Current result | What it shows | Next proof
Question flow | Working locally | Policy → answer or handoff | Security review
App tests | 17 passed | Expected demo rules | Integration tests
Source search | 32/32 found | Word-match cases | Real questions
No-answer cases | 4/4 sent to a person | No source matched | Reworded questions
Access checks | 0 in tests | Scripted cases only | Company access review
Live users | Not measured | No employee pilot | Set baseline
Time saved | Not measured | Business assumption | Pilot time study
Microsoft access | Not tested | Connection code only | Work-account test
Teams app | Not built | No Teams app | Choose workflow host
The demo checks its rules against fictional records.
It does not measure answer accuracy, employee value, company security, or production reliability.
How to read this
Notes: Sources: evaluations/latest_results.json and the Business Case. The table distinguishes implemented local behavior, synthetic tests, planning assumptions, and future evidence required.

## Slide 10: Illustrative annual time value and cost
Chart: AED thousands
| Low | Base | High
Time value | 125 | 700 | 1611
Annual cost | 740 | 740 | 740
8,400 accepted answers under illustrative adoption and resolution assumptions.
Base-case use
20 minutes of active search per accepted answer; waiting is excluded.
Time counted
50,000 possible questions: 500 people × 2 per week × 50 weeks.
Question volume
Notes: Source: HumanAPI_Business_Case.pdf. 50,000 possible questions = 500 × 2 × 50. Base case: 8,400 accepted answers × 20 active minutes × AED 250/hour = AED 700,000 estimated time value. Annual operating-cost assumption is AED 740,000. Neither value is measured cash savings.

## Slide 11: Synthetic evaluation snapshot
Chart: Checks by group
| Workflow | Found source | No answer
Passed | 17 | 32 | 4
Failed | 0 | 0 | 0
36/36
All 36 search cases matched expected results.
0
Scripted tests only; not a security proof.
17 backend tests also passed. These small synthetic checks do not assess answer quality, tenant integration, performance, adoption, or saved time.
Notes: Sources: evaluations/latest_results.json and the Evaluation Report. Search suite: 32 expected retrievals plus 4 expected no-evidence cases, all passed. Backend: 17 tests passed. These are small synthetic checks, not semantic answer-quality, penetration, or production-security evaluations.

## Slide 12: Proposed 10-week path to a small team trial
Safety review
Review data and file controls. Pick one willing team and record a starting point.
Microsoft access test
Test work-account sign-in and file access. Choose Teams or Copilot Studio.
Small team trial
Run with one willing team. Measure time, trust, accepted answers, and access issues.
Weeks 0–2
Weeks 2–6
Weeks 6–10
Notes: This is a proposed sequence, not a committed schedule. Weeks 0–2 cover safety review and choosing a willing team; weeks 2–6 test Microsoft sign-in and file access; weeks 6–10 allow a small trial only if security review and tenant access are ready.

## Slide 13: Indicative work sequence; approvals come first
Review | Set limits | Microsoft test | Workflow | Pilot
Set up Teams or Copilot workflow
Measure before and during trial
Small opt-in team trial
Check each person's file access
Test Microsoft work sign-in
Security and privacy review
Notes: Source: proposed roadmap in the Idea Document and project plan. Timing is indicative: 0–2 weeks for review, 2–6 for Microsoft proof, and 6–10 for a small pilot. It depends on security approval, tenant access, and a willing team; it is not a committed schedule.

## Slide 14: Leadership decisions
Approve a security and Microsoft access review.
Choose one low-risk, willing team for a small trial.
Measure value; stop if anyone sees a file they should not.
Notes: Decision request synthesized from the Business Case, Security Architecture, and roadmap. The pilot should proceed only after security/privacy approval and evidence that requester permissions are preserved. Stop and remediate if an unauthorized disclosure occurs.